## Sheet1
Stakeholder Communication and Complaints Register Project: Beryl Solar Farm
Date | Time | Method of contact (phone, letter, email) | Stakeholder Name | Details | Received by | Action taken by Downer (or why no action was taken) | Date issue closed
2018-08-07 | 13:10 | Phone | Anonymous | Query regarding commencement of Construction Works prior to DPE Approval | DPE - B.Schultz - N.Roworth | Downer Rep met State Department Rep on Site to discuss. Only Test Piling had been undertaken - in accordance with Development Consent. | 2018-08-08
2018-08-23 | 1:30 | Phone (Hotline) | Allan Griffin | Complaint regarding Flashing lights operating past 18:00 | Hotline - N.Roworth | Downer Project Manager made contact with complainant 23/08/2018 and notified Flashing Lights will not be operating past 18:00. This requirement communicated across Downer Leadership Team within Weekly Meeting 23/08/2018 11:30am. Email across Project Leadership Team notifying Flashing Lights not to be used after 18:00 & Compound Lights to be switched off by last person on site. | 2018-08-23
2018-08-29 | 21:06 | Text - N.Roworth | Allan Griffin | Is it necessary to have the generator and things still going at this tim of night | N.Roworth | Communication between Downer and First Solar with agreement for Downer Compound Generator to be switched off by last Downer person on site until a Sea Container is placed to deflect noise from the Stakeholders residence. | 2018-08-30
2018-09-03 | 17:32 | Phone Msg (T.Best, First Solar) | Allan Griffin | Voice Message: "What is this Fluro Orange mesh for? Are you trying to piss me off? | Tom Best (First Solar) | T.Best rang Allan at 18:31 and explained it was for sedimentation control and is required to be installed throughout the construction period as per Enviromental Management requirement. | 2018-09-03
2018-10-16 | 23:59 | Email | Dennis Armstrong | Query regarding westerly view from property at Black Lead Lane, Gulgong. | Bjorn Schultz (First Solar) | B.Schultz conducted a site assessment and it is not expected to have views of the solar farm from this property. | 2018-10-30
2018-11-03 | 9:17 | Phone - N Roworth | Lisa Swan | Phone call equiry as to what time piling operations are on Weekends? Lisa thought weekends were all quiet works. Nathan informed Lisa the orginal DA time is 8am - 1pm only on Saturdays and quiet works outside of that time | N.Roworth | Nathan informed Lisa that there are more Piling Rigs than scheduled to finish the Piling Sooner - in Approx 7 weeks (prior to Christmas) Nathan Apologised and said he understood her point of view. Ensure Operations of Piling are within the specified times - 1st piling started today at 8:01am | 2018-11-03
2018-12-06 | 16:41 | Phone - N Roworth | Lisa Swan | Phone call regarding Vehicles being seen speeding and cutting Corners at Beryl Road onto Castlereagh Highway. Same coming onto Beryl Road from Castlereagh Highway | N.Roworth | Nathan thanked Lisa for letting him know. A Downer representative was sent directly to the Corner of Beryl Road and Castlereagh Highway that afternoon to observe driving behavours. On this particular day there had been an accident on the Castlereagh Highway Bridge, there were alot of Maintenance Vehicles, Safety Vehicles and road closed signs present, no reckless behavour observed this Day, so may not be a true reflection. A Downer representative will continue to attend the Corner for observations on random days for both morning and afternoon traffic observations | Ongoing monitoring
2018-12-07 | 10:15 | Phone - N Roworth | Doug Marsh | Reported Trucks missing the Beryl Site enterance and performing U Turns in front of this Residence - an inspection was made | N.Roworth | Downer to send a representative to rectify grass damage caused by a Truck performing a U Turn | 2018-12-10
2019-01-16 | 14:58 | Phone | Darryl Benson | Please return my call regarding the dust from this dirty filthy Beryl Solar Farm, it is choking us and has been dreadful ever since you turned up. "Phone Number". You better start watering up there. | N.Roworth | N.Portess spoke with Darryl 17:10 with apology for the dust issues and notification an additional 40,000Litre watercart had been on site for the day to assist in controlling the dust. This would be continuing throughout the heat wave and as required. Darryl was informed the re-seeding has taken place with ongoing watering - hoping for rain to assist in germination. It was noted the high temperatures in combination with windy conditions this afternoon had exacerbated dust issues. N.Potess asked Darryl if he had been contacted previously in association with BSF. Darryl attended some early meetings associated with the Project however hadn't been concated by anyone associated. Darryl advised to contact N.Portess with any further issues. | 2019-01-16
2019-03-04 | 20:00approx | Text / Verbal | Mudgee Community | Downer were notified by a number of parties - Mudgee Community Facebook Post referring to Beryl Solar Farm employees being involved in theft from Coles in Mudgee. Photographic evidence of the vehicle involved was passed to Downer as part of these communications. | N.Portess | Downer identified the vehicle involved parked in a Project pickup area - the vehicle was verified by a member of the Community who witnessed the Theft incident. Photos of the IP's (Involved Persons) were attained from Coles CCTV. Following assistance from Mudgee Police, the vehicle owner was confirmed as a Project Employee who knew of the Incident and did not report. This employee was interviewed in line with the investigation and the two personnel directly involved in the thieft were subsequently identified. All three personnel were removed from the Project with notified identifications forwarded across other Downer Projects as DO NOT REHIRE. NOTE: Due to advisement by other Beryl Solar Farm employees the two IP's attended Mudgee Police station with subsequent attendance at Coles Mudgee and payment of the outstanding Account. Beryl Solar Farm broadcast the following Site Notificatoin Alert across all Project Employees: "Date: 07/03/2019 Description: Theft There have been a number of issues over recent weeks around theft: . Reports of money stolen from personnel bags on site . Reports of theft within Local Businesses identified as Beryl Solar Farm employees Theft WILL NOT BE TOLERATED on our Project. It sends a bad name across both the Beryl Solar Farm Project and all those Team Members who are doing the right thing and contributing honestly to the local community. Three personnel have been removed from the Project as of yesterday for this behaviour. These personnel names will be communicated across Downer and applicable companies as DO NOT REHIRE. Should you notice any dishonest activities report to your Leadership. Reports will be managed confidentially. Thanks to those personnel who contributed to the active management of this disappointing occurrence." | 2019-03-07
2019-03-14 | 9:00 | Email | Mudgee Community | Downer were contacted by a Motel Owner within the Mudgee community. The Motel had required to remove a number of personnel from accommodation due to the Motel being booked out in advance. The owner had given adequate notice across all tenants however there was refusal or reluctance by a number of them to vacate. Subsequently, due to insistence they must vacate, an unsavoury review of the Motel was posted on Trip Advisor by one of the removed Tenants who had previously worked on the Beryl Solar Farm Project. | N.Roworth | Downer Management met with the Motel owners and discussed the incident. Investigation was implemented by Downer to identify the remaining personnel on the Project with subsequent communication across these personnel by Delivery Partner HSE. These Team Members were removed from the Project by the Delivery Partner. NOTE: As the initial report had been submitted by the previous employees mother, Trip Advisor administration removed the review. | 2019-03-28
2019-03-22 | 16:20 | Phone | D.Benson | Message received querying around the extent of watering being conducted onProject due to significant dust at Community members residence. | N.Roworth | 27/03/2019 N.Roworth contacted D.Benson by phone and discussed the matter. Discussion around Whirlywinds generating dust and the day of the complaint being a significant wind storm followed by a large rain event. Community member informed the Project has implemented Site Controls - all Vehicles to remain on established roads - 2x LV's safely able to pass. LV's to give way to Mobile Plant, pull to side of the road and stop to reduce dust generation. 3 Watercarts were on site on the day of the event. On the day of the complaint it was observed by Downer Management & First Solar the wind event was kicking up dust in nearby paddocks as well as the Project areas. The rain event following the dust storm has assisted greatly in reducing the dust generation. Ongoing watering continuing. | 2019-03-27
2019-03-22 | 17:12 | Phone | J.Adams | Community Member query - a person observed installing Red Flags and Electrical type cabling on her property without communication prior. | N.Roworth | N.Roworth spoke with Community Member regarding installation of Red Flagging and Electrical type cabling. The Community Member informed she had spoken with Substation Management. The employee was intended to undertake the task using the roads only however had entered her property. The employee was part of the conversation and agreement between all parties of communication protocol to be established prior to entering anyones property. | 2019-03-22